## WBS
Summary | Work Category | Start Date | Due Date | Closed Date | Estimates | Resources | Time Planned | Time Spent
Inception |  | 2015-05-11 | 2015-05-15 | 2015-05-15 |  |  | 70 | 74
Project Context |  | 2015-05-11 | 2015-05-12 | 2015-05-12 | 3 | 15 | 15 | 20
Identify Project Goal | Analysis |  | 2015-05-12 | 2015-05-12 | 1 | 5 | 5 | 10
Business & Market Context | Analysis |  | 2015-05-12 | 2015-05-12 | 1 | 5 | 5 | 5
Organizational Context | Analysis |  | 2015-05-12 | 2015-05-12 | 1 | 5 | 5 | 5
Analysis & Design |  | 2015-05-11 | 2015-05-15 | 2015-05-15 | 11 | 20 | 55 | 54
Use case analysis | Analysis |  | 2015-05-15 | 2015-05-15 | 3 | 5 | 15 | 10
Functional Requirements | Analysis |  | 2015-05-15 | 2015-05-15 | 3 | 5 | 15 | 16
Quality Attributes | Analysis |  | 2015-05-15 | 2015-05-15 | 4 | 5 | 20 | 20
Environment Setup | Implementation |  | 2015-05-15 | 2015-05-15 | 1 | 5 | 5 | 3
Mento Meeting | Analysis |  |  | 2015-05-28 |  |  |  | 5
Elaboration & Construction |  | 2015-05-18 | 2015-06-13 |  | 151 | 36 | 326 | 375
Preparing Initial Presentation | Implementation |  | 2015-05-20 | 2015-05-19 | 5 | 5 | 25 | 39
Analysis & Design |  | 2015-05-20 | 2015-05-30 | 2015-06-07 | 20 | 30 | 88 | 157
System Context | Architecture | 2015-06-01 | 2015-05-21 | 2015-06-03 | 2 | 5 | 10 | 17
Static Perspective | Architecture |  | 2015-05-27 | 2015-06-04 | 3 | 5 | 15 | 20
Dynamic Perspective | Architecture |  | 2015-05-27 | 2015-06-05 | 3 | 5 | 15 | 24
Physical Perspective | Architecture |  | 2015-05-27 | 2015-06-05 | 3 | 5 | 15 | 10
Pattern and Tactics | Architecture |  | 2015-05-28 | 2015-06-05 | 4 | 5 | 20 | 20
Interface Design | Architecture | 2015-06-01 | 2015-05-30 | 2015-06-04 | 2 | 2 | 4 | 15
Data & Protocol Design | Architecture | 2015-06-01 | 2015-05-30 | 2015-06-07 | 3 | 3 | 9 | 15
Mento Meeting | Architecture |  |  | 2015-06-03 |  |  | 0 | 5
Mento Meeting | Architecture |  |  | 2015-06-12 |  |  | 0 | 5
Planning | Architecture |  |  | 2015-06-19 |  |  |  | 2
Experiments | Architecture |  |  | 2015-06-19 |  |  | 0 | 24
Element Details - User Application |  | 2015-06-01 | 2015-06-13 |  | 41 | 1 | 41 | 79
Design | Architecture |  | 2015-06-06 | 2015-06-05 | 15 | 1 | 15 | 8
Implementing | Implementation |  | 2015-06-11 | 2015-06-14 | 20 | 1 | 20 | 60
- CLI status diagram design and implementation - Modeling | Implementation | [6 empty] | 11
- Event Bus(MQTT) connection (pub/sub) | Implementation | [6 empty] | 10
- Web server (user accout manager) connection | Implementation |  |  | 2015-06-13 |  |  |  | 15
- USE case (functional impementation) | Implementation | [6 empty] | 13
- Alternative GUI | Implementation | [6 empty] | 11
Testing | Test & Debug |  | 2015-06-13 | 2015-06-20 | 6 | 1 | 6 | 11
Element Details - SA Node |  | 2015-06-01 | 2015-06-13 |  | 41 | 2 | 82 | 35
Design | Architecture |  | 2015-06-06 | 2015-06-08 | 15 | 2 | 30 | 7
Implementing | Implementation |  | 2015-06-11 | 2015-06-17 | 20 | 2 | 40 | 13
Testing | Test & Debug |  |  | 2015-06-20 | 6 | 2 | 12 | 15
Element Details - IoT System |  | 2015-06-01 | 2015-06-13 |  | 41 | 2 | 82 | 45
Design | Architecture |  | 2015-06-06 | 2015-06-07 | 15 | 2 | 30 | 15
Implementing | Implementation |  | 2015-06-11 | 2015-06-22 | 20 | 2 | 40 | 20
Testing | Test & Debug |  | 2015-06-13 | 2015-06-22 | 6 | 2 | 12 | 10
Test and Experiments |  | 2015-06-01 | 2015-06-13 |  | 8 | 1 | 8 | 20
Integration Test | Test & Debug |  | 2015-06-13 | 2015-06-23 | 4 | 1 | 4 | 12 | 6
Stress Test | Test & Debug |  | 2015-06-13 | 2015-06-23 | 4 | 1 | 4 | 8 | 6
Transition |  | 2015-06-15 | 2015-06-25 |  | 75 | 6 | 180 | 179
Acceptance Test |  | 2015-06-15 | 2015-06-25 |  | 30 |  | 90 | 68
Functional Test and Debugging | Test & Debug |  | 2015-06-25 | 2015-06-23 | 15 | 3 | 45 | 33 | 30
Quality Attribute Test and Debugging | Test & Debug |  | 2015-06-25 | 2015-06-23 | 15 | 3 | 45 | 35 | 35
Documentation |  | 2015-06-15 | 2015-06-25 |  | 45 | 6 | 90 | 111
Release and Packaging | Implementation |  | 2015-06-25 | 2015-06-25 | 15 | 2 | 30 | 10 | 10
Final Documentation Release | Documentation | 2015-06-09 | 2015-06-25 | 2015-06-24 | 15 | 2 | 30 | 71 | 25
Final Rehersal | Documentation |  | 2015-06-25 | 2015-06-25 | 15 | 2 | 30 | 20 | 20
Mento Meeting | Documentation |  |  | 2015-06-19 |  |  |  | 5
Mento Meeting | Documentation |  |  | 2015-06-25 |  |  |  | 5 | 5
Total | [6 empty] | 576 | 628

## Time Assigned
Analysis | Architecture | Implementation | Test & Debug | Documentation | Total
65 | 163 | 160 | 128 | 60 | 576
[5 empty] | Analysis | Architecture | Implementation | Test & Debug | Documentation | Total
[5 empty] | 65 | 163 | 160 | 128 | 60 | 576
[5 empty] | 71 | 187 | 145 | 124 | 101 | 628
[5 empty] | -6 | -24 | 15 | 4 | -41 | -52

## Time Spent
Analysis | Architecture | Implementation | Test & Debug | Documentation | Total
71 | 187 | 205 | 124 | 101 | 688

## Earned Value
Date | Planned | Spent | Earned |  | Planned | Spent | Earned
2015-05-11 | 14 | 10 | 12 |  | 14 | 10 | 12
2015-05-12 | 14 | 24 | 13 |  | 28 | 34 | 25
2015-05-13 | 14 | 0 | 0 |  | 42 | 34 | 25
2015-05-14 | 14 | 22 | 23 |  | 56 | 56 | 48
2015-05-15 | 12 | 0 | 0 | DAYOFF | 68 | 56 | 48
2015-05-16 | 0 | 0 | 0 | DAYOFF | 68 | 56 | 48
2015-05-17 | 0 | 0 | 0 | DAYOFF | 68 | 56 | 48
2015-05-18 | 15 | 25 | 10 |  | 83 | 81 | 58
2015-05-19 | 15 | 25 | 15 |  | 98 | 106 | 73
2015-05-20 | 15 | 25 | 10 |  | 113 | 131 | 83
2015-05-21 | 0 | 0 | 0 | MOVING | 113 | 131 | 83
2015-05-22 | 0 | 0 | 0 | MOVING | 113 | 131 | 83
2015-05-23 | 0 | 0 | 0 | MOVING | 113 | 131 | 83
2015-05-24 | 0 | 15 | 10 |  | 113 | 146 | 93
2015-05-25 | 15 | 10 | 5 |  | 128 | 156 | 98
2015-05-26 | 15 | 14 | 10 |  | 143 | 170 | 108
2015-05-27 | 15 | 20 | 10 |  | 158 | 190 | 118
2015-05-28 | 15 | 20 | 0 |  | 173 | 210 | 118
2015-05-29 | 15 | 0 | 0 | EXAM | 188 | 210 | 118
2015-05-30 | 15 | 4 | 2 |  | 203 | 214 | 120
2015-05-31 | 0 | 8 | 0 |  | 203 | 222 | 120
2015-06-01 | 15 | 16 | 0 |  | 218 | 238 | 120
2015-06-02 | 15 | 2 | 5 |  | 233 | 240 | 125
2015-06-03 | 15 | 5 | 15.5 |  | 248 | 245 | 140.5
2015-06-04 | 15 | 16 | 35 |  | 263 | 261 | 175.5
2015-06-05 | 15 | 2 | 50 | EXAM | 278 | 263 | 225.5
2015-06-06 | 15 | 4 | 0 |  | 293 | 267 | 225.5
2015-06-07 | 0 | 11 | 28 |  | 293 | 278 | 253.5
2015-06-08 | 15 | 13 | 5 |  | 308 | 291 | 258.5
2015-06-09 | 15 | 15 | 0 |  | 323 | 306 | 258.5
2015-06-10 | 15 | 14 | 0 |  | 338 | 320 | 258.5
2015-06-11 | 15 | 9 | 0 |  | 353 | 329 | 258.5
2015-06-12 | 15 | 5 | 5 | EXAM, Mentor | 368 | 334 | 263.5
2015-06-13 | 15 | 22 | 10 |  | 383 | 356 | 273.5
2015-06-14 | 0 | 26 | 10 |  | 383 | 382 | 283.5
2015-06-15 | 18 | 15.5 | 0 |  | 401 | 397.5 | 283.5
2015-06-16 | 20 | 15 | 0 |  | 421 | 412.5 | 283.5
2015-06-17 | 20 | 34 | 30 |  | 441 | 446.5 | 313.5
2015-06-18 | 20 | 2 | 0 | EXAM | 461 | 448.5 | 313.5
2015-06-19 | 20 | 7 | 0 | EXAM, Mentor | 481 | 455.5 | 313.5
2015-06-20 | 15 | 36 | 12 |  | 496 | 491.5 | 325.5
2015-06-21 | 0 | 11 | 18 |  | 496 | 502.5 | 343.5
2015-06-22 | 20 | 40 | 52 |  | 516 | 542.5 | 395.5
2015-06-23 | 20 | 30 | 90 |  | 536 | 572.5 | 485.5
2015-06-24 | 20 | 30 | 30 |  | 556 | 602.5 | 515.5
2015-06-25 | 20 | 25 | 60 |  | 576 | 627.5 | 575.5

## Jangsu
Date | Category | Time(Hour) | Comments
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31 | Analysis | 1.5 | ADS refine
2015-05-31 | Architecture | 0.1 | Design what?
2015-06-01 | Architecture | 4 | 1st Decoposition
2015-06-02 |  | 0 | WaterFront shopping
2015-06-03 | Architecture | 1 | Mentor meeting
2015-06-04 | Architecture | 3 | decomposition and make a topic for pub/sub
2015-06-05
2015-06-06
2015-06-07 | Architecture | 1 | Interface 회의
2015-06-07 | Documentation | 2 | Sequence Diagram
2015-06-08 | Implementation | 4 | HTTP client
2015-06-09 | Implementation | 4 | HTTP client
2015-06-10 | Implementation | 2 | HTTP client
2015-06-11 | Test & Debug | 3 | HTTP client
2015-06-12 | Architecture | 1 | Mento meeting
2015-06-13 | Test & Debug | 1 | Web server connection
2015-06-13 | Architecture | 2 | Planning
2015-06-14 | Test & Debug | 2 | Test case refine & Test
2015-06-14 | Implementation | 1 | Log set/get/view by HTTP I/F
2015-06-14 | Documentation | 1 | System Context
2015-06-15 | Test & Debug | 2 | Test case refine & Test
2015-06-15 | Test & Debug | 2 | Web server connection
2015-06-16 | Documentation | 1 | Test case refine
2015-06-16 | Documentation | 2 | 1st Decomposition of IoT system
2015-06-17 | Documentation | 7 | Refine design document, freeze 1.0
2015-06-18 | Documentation | 2 | Refine documents
2015-06-19 | Documentation | 2 | Refine documents
2015-06-19 | Architecture | 1 | Mentor meeting
2015-06-20 | Test & Debug | 3 | Functional Test and Debugging
2015-06-20 | Documentation | 4 | Final Documentation Release
2015-06-21 | Documentation | 1 | Final presentation flow desicion | DOCUMENTS
2015-06-22 | Test & Debug | 6 | Functional Test and Integration TEST with QA
2015-06-23 | Test & Debug | 7 | Functional Test and Integration TEST with QA
2015-06-24 | Documentation | 8 | Documentation and rehersal
2015-06-25 | Documentation | 6 | Documentation and rehersal

## KIM
Date | Category | Time(Hour) | Comments
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31 | Analysis | 1.5 | ADS refine
2015-05-31 | Architecture | 1 | UI decomposition
2015-06-01 | Architecture | 4 | 1st Decoposition
2015-06-02 |  | 0 | WaterFront shopping
2015-06-03 | Implementation | 3 | simple pub/sub implementation in java for UI | Event Bus
2015-06-03 | Architecture | 1 | Mentor meeting
2015-06-04 | Architecture | 3 | decomposition and make a topic for pub/sub
2015-06-04 | Implementation | 0.5 | make CLI status diagram | CLI Modeling
2015-06-05 | Implementation | 2 | UI implementation - preparing MVC in JAVA | CLI Modeling
2015-06-06
2015-06-07 | Implementation | 5 | UI implementation - MVC + MQTT | CLI Modeling
2015-06-08 | Implementation | 5 | UI implementation - SANode modeling | Event Bus
2015-06-09 | Implementation | 5 | UI implementation - pub/sub wtih SANode (json) | USE CASE
2015-06-10
2015-06-11 | Architecture | 1 | Review Design Document
2015-06-12 | Architecture | 1 | Mento meeting
2015-06-13 | Implementation | 3 | User APP Implementation - USE Case | USE CASE
| Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-14 | Implementation | 4 | User APP Implementation - USE Case | USE CASE
| Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-15 | Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-16 | Documentation | 2 | Arch. Design for User App.
2015-06-17 | Documentation | 7 | Arch. Design for User App.
2015-06-18
2015-06-19 | Architecture | 1 | Mentor meeting
2015-06-20 | Implementation | 4 | USE CASE - Sharing | USE CASE
| Test & Debug | 3 | JAVA freeze bug fix and Demo. scenario | TEST & DEBUG
| Documentation | 1 | Seq. Diagram for API. | DOCUMENTS
2015-06-21 | Documentation | 1 | Final presentation flow desicion | DOCUMENTS
2015-06-22 | Test & Debug | 7 | QA and Functional TEST
2015-06-23 | Test & Debug | 5 | QA and Functional TEST
2015-06-24 | Documentation | 2 | Documents refine and rehersal
2015-06-25 | Documentation | 7 | Documents refine and rehersal

## LIM
Date | Category | Time(Hour) | Comments
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31 | Analysis | 1.5 | ADS refine
2015-05-31 | Architecture | 0.1 | Design what?
2015-06-01 |  | 0 | Hospital
2015-06-02 |  | 0 | WaterFront Meeting
2015-06-03 | Architecture | 1 | Mentor meeting
2015-06-04 | Architecture | 3 | decomposition and make a topic for pub/sub
2015-06-05
2015-06-06
2015-06-07 | Architecture | 1 | Define SA Node Interface
2015-06-08 | Architecture | 1 | Refine SA Node Interface
2015-06-08 | Architecture | 1 | SA Node Static Diagram
2015-06-09 | Implementation | 3 | SA Node Program
2015-06-10 | Implementation | 3 | SA Node Re Structure
2015-06-11 | Architecture | 1 | Review Design Document
2015-06-12 | Architecture | 1 | Mento meeting
2015-06-13 | Implementation | 3 | SA Node Implementation
2015-06-13 | Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-14 | Implementation | 4 | SA Node Implementation
2015-06-14 | Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-15 | Test & Debug | 2 | Test&Debugging - USE CASE
2015-06-15 | Architecture | 1 | Design Static View of SA Node
2015-06-16 | Architecture | 4 | Design Dynamic View of SA Node
2015-06-16 | Documentation | 2 | Refine SA Node Interface
2015-06-17 | Documentation | 6 | Refine SA Node Interface
2015-06-18
2015-06-19 | Architecture | 1 | Mentor meeting
2015-06-20 | Test & Debug | 7 | SA node Testing
2015-06-21 | Documentation | 1 | Final Presentation Scenario
2015-06-22 | Test & Debug | 7 | Functional and QA test
2015-06-23 | Test & Debug | 9 | Functional and QA test
2015-06-24 | Documentation | 2 | Airchtectural Documents
| Test & Debug | 3 | Stress TEST and QA TEST
2015-06-25 | Documentation | 3 | Airchtectural Documents
| Test & Debug | 2 | Stress TEST and QA TEST

## HONG
Date | Category | Time(Hour) | Comments
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31 | Analysis | 1.5 | ADS refine
2015-05-31 | Architecture | 0.1 | Design what?
2015-06-01 | Architecture | 4 | 1st Decoposition
2015-06-02 | Analysis | 1 | Use case refine
2015-06-03 | Architecture | 1 | Mentor meeting
2015-06-04 | Architecture | 3 | decomposition and make a topic for pub/sub
2015-06-05
2015-06-06
2015-06-07
2015-06-08
2015-06-09 | Documentation | 1 | Documentation
2015-06-10 | Documentation | 2 | Documentation
2015-06-11 | Documentation | 3 | Documentation
2015-06-12 | Architecture | 1 | Mento meeting
2015-06-13 | Documentation | 3 | Documentation
2015-06-14 | Architecture | 3 | App design | --> Experiment
2015-06-15 | Architecture | 3 | App design | --> Experiment
2015-06-16 | Architecture | 3 | App design | --> Experiment
2015-06-17 | Documentation | 6 | Documentation
2015-06-18
2015-06-19 | Architecture | 1 | Mentor meeting
2015-06-20 | Implementation | 5 | Android App based GUI
2015-06-20 | Documentation | 2 | Final Documentation Release
2015-06-21 | Implementation | 3 | Android App based GUI
2015-06-21 | Documentation | 1 | Final Presentation Scenario
2015-06-22 | Documentation | 5 | Documentation for delivering
| Test & Debug | 4 | User App Testting for Android phone
2015-06-23 | Documentation | 5 | Documentation for delivering
| Test & Debug | 4 | User App Testting for Android phone
2015-06-24 | Documentation | 8 | Documentation for delivering
| Test & Debug | 2 | User App Testting for Android phone
2015-06-25 | Test & Debug | 2 | User App Testting for Android phone
| Documentation | 6 | Documentation for delivering

## LEE
Date | Category | Time(Hour) | Comments
2015-05-11
2015-05-12
2015-05-13
2015-05-14
2015-05-15
2015-05-16
2015-05-17
2015-05-18
2015-05-19
2015-05-20
2015-05-21
2015-05-22
2015-05-23
2015-05-24
2015-05-25
2015-05-26
2015-05-27
2015-05-28
2015-05-29
2015-05-30
2015-05-31 | Analysis | 1.5 | ADS refine
2015-05-31 | Architecture | 4 | Arduino MQTT Library Feasibility Test
2015-06-01 | Architecture | 4 | 1st Decoposition
2015-06-02 | Test & Debug | 1 | Java with WebSocket / MQTT Experiments
2015-06-03 | Architecture | 1 | Mentor meeting
2015-06-04 | Architecture | 3 | decomposition and make a topic for pub/sub
2015-06-05
2015-06-06 | Architecture | 4 | server component decomposition
2015-06-07 | Architecture | 5 | REST API specification for account manager & log viewer
2015-06-08 | Architecture | 3 | Experiment deploy of web server (google app engine)
2015-06-09 | Implementation | 2 | Experiment web server framework (flask and pony orm)
2015-06-10 | Implementation | 7 | REST API implementation
2015-06-11 | Architecture | 1 | Review Design Document
2015-06-12 | Architecture | 1 | Mento meeting
2015-06-13 | Test & Debug | 5 | REST API unittest (pytest)
2015-06-13 | Architecture | 1 | mongoDB experiment
2015-06-14 | Architecture | 2 | Add Static Perspective
2015-06-14 | Implementation | 5 | SMTP manager implementation
2015-06-15 | Implementation | 2 | Add Heartbeat monitoring daemon
2015-06-15 | Architecture | 2 | Angular.js experiment
2015-06-16 | Test & Debug | 2 | Virtual node implementation
2015-06-16 | Architecture | 2 | Angular.js experiment
2015-06-17 | Documentation | 8 | Refine IoT Server Design
2015-06-18
2015-06-19 | Architecture | 1 | Mentor meeting
2015-06-20 | Implementation | 4 | WEB(Browser) GUI
2015-06-20 | Test & Debug | 3 | IoT Server
2015-06-21 | Implementation | 3 | WEB(Browser) GUI
2015-06-21 | Documentation | 1 | Final Presentation Scenario
2015-06-22 | Test & Debug | 5 | Integration TEST
2015-06-23 | Test & Debug | 10 | Web paging TEST
2015-06-24 | Test & Debug | 2 | Integration TEST
| Documentation | 8 | preparing the Demo senario
2015-06-25 | Documentation | 6 | Architectual rehersal
| Test & Debug | 2 | TEST and debugging